## React Native
Module / Feature | Estimated Days | Cumulative Days | Stretched Days | Start Week | End Week
Splash Screen | 2 | 2 | 5 | 1 | 1
Login/Signup with OTP | 4 | 6 | 10 | 1 | 3
Home Screen - Match & Contest List | 5 | 11 | 13 | 3 | 5
Contest Detail Screen | 3 | 14 | 8 | 5 | 6
Join Contest Flow | 4 | 18 | 10 | 7 | 8
Team Creation (Player Selection) | 6 | 24 | 16 | 8 | 11
Live Match Centre (Scores, Leaderboard) | 7 | 31 | 18 | 11 | 14
Wallet Management | 5 | 36 | 13 | 14 | 16
KYC Upload & Verification | 5 | 41 | 13 | 16 | 18
Refer & Earn | 3 | 44 | 8 | 18 | 19
Notifications (Reminders, Payments) | 3 | 47 | 8 | 20 | 21
Profile Management | 3 | 50 | 8 | 21 | 22
Help & Support + Rules Section | 2 | 52 | 5 | 22 | 23
Testing & QA | 6 | 58 | 16 | 23 | 26
UAT & Store Deployment | 6 | 64 | 16 | 26 | 28

## Node.js
Module / Feature | Estimated Days | Cumulative Days | Stretched Days | Start Week | End Week
Login/Signup with OTP (Backend) | 2 | 2 | 8 | 1 | 2
Home Screen Data API | 2 | 4 | 8 | 2 | 3
Contest Details & Join Logic API | 3 | 7 | 12 | 3 | 5
Team Creation & Validation API | 3 | 10 | 12 | 5 | 7
Live Score Sync & Points Calc API | 4 | 14 | 16 | 7 | 10
Wallet Transactions & Balance API | 3 | 17 | 12 | 10 | 12
KYC Handling API | 3 | 20 | 12 | 12 | 14
Refer & Earn Logic | 2 | 22 | 8 | 14 | 15
Notifications API | 2 | 24 | 8 | 15 | 16
User Profile API | 2 | 26 | 8 | 17 | 18
Support / Rules API | 1 | 27 | 4 | 18 | 18
Admin Panel API Support | 5 | 32 | 20 | 19 | 22
Reports & CSV Exports | 3 | 35 | 12 | 22 | 24
Testing & QA | 6 | 41 | 25 | 24 | 28

## React.js
Module / Feature | Estimated Days | Cumulative Days | Stretched Days | Start Week | End Week
Admin Login & Dashboard | 3 | 3 | 19 | 1 | 4
Contest Management | 4 | 7 | 25 | 4 | 8
User Management & KYC | 4 | 11 | 25 | 8 | 12
Finance Management | 4 | 15 | 25 | 12 | 16
CMS - Banners & Promotions | 3 | 18 | 19 | 16 | 19
Push Notifications Panel | 2 | 20 | 12 | 19 | 21
Reports & Exports | 3 | 23 | 19 | 21 | 24
Testing & QA | 4 | 27 | 25 | 25 | 29